Synopsys of the migration process (there is more in it) to be implemented with the help of certified professionals.
Migration, Step by Step
Communicating the change
Starting the migration process
Providing training and support
Deploying LibreOffice on PCs
The deployment of LibreOffice needs to be planned in advance and should be coord-inated with the training schedule, in order to ensure that users will be able to use the software after the first training session.
The deployment method can be selected according to the IT infrastructure. LibreOf-fice can be mass deployed on Windows by tweaking the .MSI package, and creating a Group Policy Object (GPO) to distribute the software package.
Deploying LibreOffice does not mean era-dicating MS Office from each and every PC. The goal is to maximize the number of PCs using LibreOffice, and foster the interop-erability with MS Office by identifying the areas where the latter tries to perpetuate the lock-in.
It will be necessary to educate all users to rely on the ODF document standard to ex-change files both internally and externally, as this is the only way to ensure true inter-operability, and replace proprietary fonts with free fonts to avoid “visual” issues.
The Document Foundation suggests to de-ploy LibreOffice in large organizations with the backing of professional support by cer-tified people (list available on website).
Lessons from successful migrations
LibreOffice feature set is more than adequ-ate for the everyday needs of the majority of the users inside organizations. In gene-ral, the few technical obstacles are related to very complex documents, or to spread-sheets using advanced features, or to MS Office macros, which are often difficult to migrate for a number of reasons.
Users should be able to produce docu-ments using LibreOffice right after the trai-ning: therefore, it is crucial to complete the set up and the test of the workstations be-fore the training begins, as any delay in the installation of LibreOffice will diminish the effect of the training itself. It is also extre-mely important to offer a reference point for any problem connected to the migra-tion, starting from "technology leaders" up to trained support personnel.
The production of the first documents will create a positive perception about the quality of LibreOffice: a smooth process will motivate users to continue and try more advanced features, while stumbling into an issue will leave a negative feeling.
The biggest problem is resistance to chan-ge, which is a side effect of the introduct-ion of a new technology in every large or-ganization. This it seen as a burden in ad-dition to every day’s work, and has to be tackled with a focused communication. Users have to be persuaded that the new tool can provide a better and more rewarding user experience.
The "brute force" method - which consists in installing LibreOffice and eradicating MS Office without any warning - is the worst of all choices, as it creates a rejection effect which kills any hope of success.

---
LibreOffice is a Free Software suite for personal productivity for MS Windows, MacOS X and GNU/Linux, offering six feature-rich applications.
LibreOffice adopts the ISO standard Open Document Format (ODF), recogni-zed by governments and organizations, and based on true open standards.
LibreOffice reads and writes Microsoft proprietary file formats, from the legacy DOC, XLS and PPT to the latest DOCX, XLSX and PPTX (Office Open XML).
LibreOffice also handles the Hybrid PDF format, a standard PDF file which em-beds an editable ODF document. These files can be opened by LibreOffice as ODF documents, and by other software as plain PDF files.
LibreOffice provides shortcuts to send documents as e-mail attachments in all available formats: ODF, PDF and MS Office formats, including legacy.
LibreOffice installs free fonts, designed to be compatible with every operating system and therefore able to further increase interoperability.
LibreOffice Migration Protocol
The protocol is a reference for migra-tions, based on best practices from some of the most successful projects (such as the city of Munich in Germany, Regione Umbria in Italy, and several enterprises and public administrations in Europe).
Some Large Migrations
City of Munich (Germany)
15,000 PCs from Windows
and MS Office to Linux and LibreOffice
Copenhagen Hospital System
25,000 PCs from MS Office to LibreOffice
Comunitat Valenciana (Spain)
120,000 PCs from MS Office to LibreOffice
French Government
500,000 PCs of 15 Ministeries from MS Office to LibreOffice
Migrating
to LibreOffice
for Enterprises
and Public
Administrations
The office suite is a key component of any enterprise workflow, and is essential for personal productivity. LibreOffice is a viable replacement for Microsoft Office, and can significantly reduce the Total Cost of Ownership of PCs in enterprises and public administrations because of the substantially lower migration cost (in comparison to the cost of the proprietary license). This short leaflet has the objective of giving an overview of the migration process, based on a number of successful European case studies.
More Information
www.libreoffice.org
blog.documentfoundation.org
info@documentfoundation.org
The Document Foundation represents the LibreOffice global community